## Instructions
1. Start with a new workbook and enter your task data as in Sheet1. Column A contains the task
descriptions, column B contains the beginning date for each task, and column C contains the
number of days to complete the task. Column D contains formulas thhat determine the ending day
for each task. For example, the formula in cell D2 is =B2-C2-1. Column D isn’t really necessary
(and is not used in the chart), but including it will tell you e
2. Create a stacked horizontal chart from the data in A2:C13. The Chart Wizard will probably guess
these series incorrectly, so you’ll need to set the category axis labels and data series manually.
The category (x) axis labels should be range A2:A13, the Series 1 data should be B2:B13, and
Series 2 data should be C2:C13.
3. Remove the chart’s legend and adjust the height of the chart so that all of the category axis
labels are visible (or, change the font to a smaller size).
4. Access the Format Axis dialog box for the horizontal (value) axis. Set the Minimum and
Maximum values to correspond to the earliest and latest dates in your project. Note that you can
enter actual dates into this dialog box. To display the dates at weekly intervals, set the Minimum to
a Monday, the Maximum to a Sunday, and the Major Unit to 7.
5. Select the data series that corresponds to the data in Column B and access the Format Data
Series dialog box. Set Borders to None and Area to None. This essentially makes the first data
series invisible – and makes the chart resemble a Gantt chart.
6. Apply other formatting as desired. For example, you may want to add gridlines and a title.
You’ll be able to adjust your project schedule and the chart will update automatically.
However, if you use dates outside of the original date range, you’ll need to change the
scaling for the horizontal (value) axis.

## Sheet1
Task | Start Date | Duration | End Date
Planning Meeting | 1997-12-29 | 1 | 1997-12-29
Develop Questionnaire | 1997-12-30 | 11 | 1998-01-09
Print and Mail Questionnaire | 1998-01-13 | 9 | 1998-01-21
Receive Responses | 1998-01-16 | 15 | 1998-01-30
Data Entry | 1998-01-16 | 18 | 1998-02-02
Data Analysis | 1998-02-03 | 4 | 1998-02-06
Write Report | 1998-02-09 | 12 | 1998-02-20
Distribute Draft Report | 1998-02-23 | 1 | 1998-02-23
Solicit Comments | 1998-02-24 | 4 | 1998-02-27
Finalize Report | 1998-03-02 | 5 | 1998-03-06
Distribute to Board | 1998-03-09 | 1 | 1998-03-09
Board Meeting | 1998-03-17 | 1 | 1998-03-17
Formulas:
End Date = [Start Date]+[Duration]-1